## Physical Plan (BED 2)
Agency : NATIONAL COUNCIL ON DISABILITY AFFAIRS/PROGRAMS MANAGEMENT DIVISION
Division : Programs Management Division
MAJOR FINAL OUTPUTS |  | ACCOMPLISHMENT (Quantity) | DESCRIPTION of RESULTS (Quality) | REMARKS
(MFOs) | CY 2013
/PROGRAMS, ACTIVITIES | PHYSICAL
and PROJECTS (PAPs) | TARGETS
MFO 1 - POLICY & PLAN FORMULATION, COORDINATION, MONITORING & EVALUATION
1. Provision of Secretariat and Technical | 7 policies | 4 policy reviewed and provided recommendation | Sub-Com on Policy Development and | RA 9344 - Juvenile Justice and Welfare Act
Assistance and Monitoring Coordination to |  |  | Legislation organized and reviewed IRR | RA 10410 - Early Years Act
the Sub-Committees under E.O. 709 |  |  | of RA 10366 | RA 10366 - IRR
Senate Bill 3002 - Establisment of
SPED Center
a. SCABET |  | 1 Draft BP 344 IRR Amendments | * Major revisions on buildings/structures | For consultations with PWD sector and
|  |  | standards/dimensions | other stakeholders
* Focused on physical/built environment
taking into considerations the ff:
- Universal design
- Needs/concerns of other disability
groups
|  | Reactivation of Sub-Committees in RCDA VI | Disability structure to fastrack the
|  | - Accessibility on Built Environment | implementation of BP 344
(Region 6 and 10)
- Transportation Accessibility (Region 6)
Formulated the Sub-Committee's Work
and Financial Plan for 2014
|  | organized the Access Audit and Monitoring | To promote implementation of BP 344
team in Region 10
|  | Organized the Iligan City Access Audit and | To promote implementation of BP 344
Monitoring Team
b. Training & Employment/Livelihood |  | 3 resolutions endorsed to the Board | Endorsed to the Board three (3) resolutions
requesting the Department of Labor and
Employment to provide desks assisting PWDs
and to encourage PWDs to join the conduct
of their regular Job Fair, circulate to all
Public Employmnet Service Office, Bureau
of Internal Revenue Offices and top
coporations the "Guidelines for the Issuance
of a Certificate of Employment as a requirement
for Employers to Avail of Tax Incentives"
and issue a Department order directing the
organization of the SCTLE at the regional
and provincial levels
|  | Reactivate the SCOTEL in Region 6 & 10 | Disability structure to facilitate provision
of TEL opportunites for PWDS
c. Children with Disabilities |  | Input to the following projects as Vice-
Chair of the Sub-Committee on Children
with Disability and other concerns on
children:
* IEC materials - 1 Poster
|  | * Harmonization of Laws UNCRC & UNCRPD | Increase of awareness of child rights against
abuse, violation and discrimination
|  | * Dev. of Communication Messages | Advocacy awareness of the general public
|  | for the 2nd National Plan of Action for | on the potentials of children with
|  | Children (NPAC) | disabilities
* Building Accessible, Inclusive Community
Playground for Children at the Rural and
Urban Areas (1 Proposal)
|  | * 1 Child Protection Policy | Submitted to CWC for Board approval
d. Health |  | One (1) Report | *NCDA recommended programs and services | Meeting with DOH schedule on
|  |  | to the DOH Health Program for PWDs during | December 13, 2013
the Consultative Meeting on the NCDPC-
Degenerative Disease Office-DOH
Strategic Plan Framework and Five Year
Strategic Plan for PWDs.
e. Access to Justice and Anti-Discrimination
* Conduct of Research with partner | 1 research/journal | 2 disability inclusion manuals formulated | * Manual on disability sensitivity for Public
Agencies/Collection of Disability |  | and endorsed | Prosecutors, and PAO formulated and endorsed
Related Researches |  |  | *Trainer's Manual on Disability sensitivity for
the PNP formulated and endorsed
f. Auxilliary Services |  | * Draft Terms of Reference (TOR) for the | The TOR will provide the Sub-Committee program
|  | Sub-Committee on Auxiliary Social Services | and policy direction on auxiliary social
services
|  | * Developed the Survey Questionnaire | the results of the survey on Available
|  | on the survey of Available Auxiliary Social | Auxiliary Social Services will serve as
|  | Services for PWDs | input for the country report for the
forthcoming ASEAN Conference for the
Evaluation of Auxiliary Social Services for PWDs.
2. Conduct of Philippine Congress on | 3 recommendations | Conduct of Pre-CBR Congress on Dec. 9-12, | -Organization of a National Congress | The CBR Congress will be held on July
CBR |  | participated in by 35 CBR practitioners/ | Working Committee and Sub-Committees | 2014 in line with the NDPR Week
|  | DPOs/NGOs | with TOR
1 network
-Draft Philippine CBR Network Constitution
and By-Laws
3. Maintenance/Strengthening of Disability | 1 back-up data on | 1. Philippine Registry Users Training | * 145 Focal persons from PDAO/MSWDO/ | One (1) Roll-out Training in Region XI
Data Base on ID Issuance (Registry)/ | registry | represented by 78 LGUs coming from 12 | CSWDO/PSWDO/CHD-DOH/DSWD Regional Office | (Davao) participated by four (4)
other related Data |  | Regions: Regions 1, 2, 6, 7, 8, 10, 11, 12, | trained on the Philippine Registry System | Provinces (Davao del Sur, Davao del
|  | CARAGA, NCR, CAR, ARMM |  | Norte, Davao Oriental and Compostella
|  |  | * Action Plan formulated by each LGU for the | Valley
Roll-out Training
2. Served as Learning Resource Provider
during the Training
|  | 3. One (1) signed MOA on the Philippine | *MOA between NCDA/DOH/DSWD re:
|  | Registry on PWDs | Philippine Registry for PWDs to support
the implementation of the DOH Philippine
Registry for Person with Disability
|  | 4. NCDA ID issued to PWDs (Jan to Nov '13) | *A total of 353 accomplished data encoded | PWD are directed to avail of the PWD ID
|  |  | to DOH Philippine Online Registry | card to their respectives LGUs
(June to November 2013)
4. Monitoring of the Implementation of | 2 reports
National and International Laws/Policies
and Commitments
5. 3rd Decade formulate of NPA - areas
assigned to PMD
MFO 2 - ADVOCACY & TECHNICAL ASSISTANCE & CAPABILITY BUILDING
1. Orientation, Training of PWDs, PNP-
Personnel (Women and Children Desk,
Day Care Workers and other Stakeholders,
Partners on:
* NHE (for expansion) | 22 LGUs | Region I (La Union) | Promoted the NHE Project in the expansion
|  | * San Juan | sites and other LGUs
* Pugo
Region IV-B
* Puerto Princesa
Region VI
* Guimbal
NCR
NHE Trainings/Seminars/Workshops
1. NHE Forum
2. NHE National Consultation
3. Disability Equality Training
4. Strategic Planning and Teambuilding
5. NHE Orientations conducted
-Laguindingan
- Manolo Fortich
-Talisayan
-El Salvador
- Camiguin
- Lugait
- Malybalay
- Anitao
- Iligan City
- Cabanatuan City
- Lanao Del Norte
- CDO City
- Gingoog City
-Misamis Occidental
6.Designation of NHE Focal Person in
DSWD Region 3
* Inclusive Education | 45 Day Care Workers
-Training of Day Care Workers on |  | 1 Training conducted |  | Only 1 Training conducted due to the
Inclusive Education - SPED Using |  | 22 Day care Workers; 2 Social Workers |  | busy schedule of DepEd (Learning
the Repackaged Modules |  | 2 Child Development Workers |  | Service Provider)
* Sign Language/Disability Sensitivity | 156 PNP Personnel |  |  | * Draft trainer's manual endorsed to
PNP, PNP to review it with a TWG and
source funding
* CBR
* Newborn Screening Filter Cards/Kits | 150 Newborn | 200 Newborn Screening Cards | Served as ëye opener" to all mothers the
| Screening Filter |  | importance of early detection and
| Cards/Kits |  | intervention of disabilities
* Orientation Seminar on Disability |  | 21 national federation of PWDs and 8 | * The PWD participants were trained on
Sensitivity and Emergency Responses |  | emergency responders/government | how to respond to emergency situations like
for PWDs (NCR) |  | agencies participated/trained/oriented | - Calling PATROL 117 for help with Actual
- Fire
- Crimes/Road Accidents
* PWD leaders'response on the training that
they would like the same orientation
seminar to be held in their own localities
Continue linkage and network with DILG's
PATROL 117
*Conference on Increasing Sensitivity |  | Eighty six (86) participants attended the | * Updated participants on current state of
Level of Parents and Caregivers of |  | Conference composed of parents/caregivers | children with disabilites to include issues
Children with Disabilities |  | professional/students and few PWDs. | and challenges
* Participants expressed/shared their views
on how government and civil society especially
how parents can help their children
develop their full potentials
2. Promotion of Sports Programs for | 75 PN athletes | *Conducted and facilitated trainings, trounaments and other | *coordinated with RCDA, GO, and NGOs for the identification of 79
PWDs in partnership with DepEd, |  | preparations for Disability Inclusive Sports | PWD athlethes
Philspada Organizations of PWDs |  |  | *Facilitated the conduct of chess training/tournament for PWDs
relative to the Philippine National games
*Facilitated the conduct the ASEAN Tenpin Bowling Tournament
*Facilitated the elimination games for the 7th ASEAN Paragames
|  |  | *Facilitates the conduct of the Strategic Planning on Disability | for conduct December
Inclusive Sports
3. Other projects/activities
* Assistive Devices |  | * 18 customized and standard wheelchairs | Improved participation of PWDsin school
|  | 11 Canes, 3 walkers, 12 pairs of clutches, | and livelihood activities
4 hearing aids
10 laptops and 7 tablets
|  | * One (1) Orientation Workshop on Disability | House of Rep. and Senate Com. Sec. sensitized
* Forum on Rights, Privileges and Benefits
( Bogy. San Lorenzo, Makati City)
|  | *Child and Youth Forum | Increase participation of children and youth
with disabilities; Plan of action and resolution
developed
|  | *Forum on "Realizing Rights of Children | Inclusion of Disability Rights for Children
Through Legislation"
|  | * Conference on Increase Sensitivity level of | Increase knowledge Parents and Caregivers
|  | Parents and Caregivers | on Disability
|  | *Meeting with DENR | Improvement of Disability-related plan
|  | * Legal Bases of Development Work | NMAP will include CWDs in education
|  | with PWDs | program
* Consultation meeting on reimbursement
of outpatient PT, OT and Speech
|  | *served as LSP on disability inclusive DRRM | *70 MMDA rescue and response personnel oriented
|  | at MMDA | on disability sensitivty in situations of risk and disaster
|  | *served as LSP on int. Day of disaster risk | *DRRM officers and PWD participants oriented on disability
|  | reduction for Taytay | inclusion in DRRM and efforts of NCDA on the matter
|  | *served as LSP on Workshop of CHR | *PWD priority issues and agenda on statistics, employment, education
|  | legislative agenda | and accessibility were incorporated with the CHR legislative concerns
|  | *served as LSP at DSWD policy study | *PWD concerns in surrogacy provided to DSWD; NCDA position on NVRC
|  | session workshop | conversion to a technical resource center emphasized
|  | *served as LSP at CCC NCCAP anchor | *Inclusive project implementation criteria as an indicator emphasized
|  | program implementation strategic | for CCC
planning workshop
|  | *served as LSP representing NCDA for | *provided inputs for the Women and Girls with Disability Chapter of the
|  | the Session WEDGE Plan | WEDGE Plan
*Facilitated the conduct for the National
Working Group of Access 2020
4. Training on Business Management |  | 29 Leaders of DPOs from 13 regions | Provide knowledge on how to start and
and Project Proposal Writing for Social |  |  | manage a business
Enterprise Development Partners
5. Pre-ASEAN Conference on Auxiliary |  | Workshop Conducted | The Output will be used on the preparation
Social Services for PWDs |  |  | of the Philippine Country report on the
ASEAN Conference for PWDs to be held
February.